Proposal

Apparel Group Enterprise Data and AI Platform on AWS

Phase 1 Proposal and Phased Roadmap

By NorthBay Solutions

July 2026

Version 3.0

Table of Contents

1. Executive Summary	3

2. Strategic Context	3

3. Phase 1 Scope: What You Get in 12 Weeks	4

3.1. Workstream 1: Data Foundation	4

3.2. Workstream 2: Price Optimization	5

3.3. Workstream 3: Inter-store Transfer	7

3.4. Workstream 4: Amazon Quick (Retail IQ)	8

3.5. Data Sources	9

4. Project Schedule	9

5. Phase 1 Investment and Team	11

5.1. Headline	11

5.2. Team Composition	12

5.3. Notes on Pricing	12

5.4. Payment	12

6. Client Responsibilities, Dependencies and Schedule Protection	12

6.1. Apparel Group Responsibilities	13

6.2. Assumptions	13

6.3. How Delays and Changes Are Handled	14

6.4. Communication and Escalation	15

7. Phase 2 Roadmap	15

7.1. Retail Use Cases at Complete Scope	15

7.2. Amazon Quick Implementation	15

7.3. Enterprise-Wide Data Lake	16

8. Out of Scope (Phase 1)	16

9. Next Steps	16

## Executive Summary

Northbay Solutions will design and deliver a foundational AWS data and AI platform for Apparel Group, built on the latest AWS Lakehouse architecture, over a 12-week Phase 1.

The engagement runs in two phases. Phase 1 lasts 12 weeks and is fully funded by AWS. It is delivered through four workstreams: Data Foundation, Price Optimization, Inter-store Transfer, and Amazon Quick. Phase 2 is funded by Apparel Group on a time-and-material basis. It continues directly from Phase 1, taking these use cases to their complete scope and extending coverage across the wider source landscape. The AWS Landing Zone is owned and delivered by the AWS ProServe team and is outside Northbay's scope; the Northbay workstreams build on it.

Phase 1 opens with a shared two-week discovery covering the two retail use cases, Price Optimization and Inter-store Transfer. During discovery we work with Apparel Group to assess the current state, complexity, and availability of the relevant data, and from that produce a Phase 1 delivery plan defining the target state, the definition of done, and what is achievable within the 12 weeks. This plan, building on the SoWs previously shared by Apparel Group, is jointly reviewed, finalized, and approved by Apparel Group within the first two weeks of Phase 1. For Amazon Quick, Apparel Group confirms the six priority data sources to connect within the same two weeks.

The approach is incremental. Each capability is built on a foundation that later work reuses, so the value delivered keeps growing well beyond the initial 12 weeks.

## Strategic Context

Apparel Group's data sits across many source systems spanning retail, e-commerce, loyalty, marketing, supply chain, and finance. Getting real value from it, whether that is analytics, modern reporting, or AI, depends on first bringing it together into a governed, cloud-native foundation on AWS.

A few points shape how we have scoped this work:

- Start with a foundation, not a big-bang build.: Phase 1 stands up the lakehouse platform once, so every use case that follows draws on the same platform instead of rebuilding plumbing each time.

- Prove value on real use cases early.: Rather than delivering a platform with nothing running on it, Phase 1 brings up Amazon Quick for natural-language access to business data and makes a start on two retail use cases that matter to the business, Price Optimization and Inter-store Transfer.

- Let the data determine the depth.: The scope of the two retail use cases depends on what the underlying data can support. We establish this in the first two weeks through a shared discovery, and then commit to a scope we are confident we can deliver.

- Build to scale beyond Phase 1.: Phase 1 is funded by AWS and time-boxed to 12 weeks. It is designed as the first step of a longer program, so the platform and patterns carry directly into Phase 2 and the wider source landscape without rework.

## Phase 1 Scope: What You Get in 12 Weeks

Phase 1 is delivered through four workstreams: Data Foundation, Price Optimization, Inter-store Transfer, and Amazon Quick. Each workstream below is described with its activities, its assumptions, and what is out of its scope.

The two retail use cases share a single two-week discovery. Its output is a Phase 1 delivery plan covering both use cases: the target state, the definition of done, and what is achievable within the 12 weeks, based on the state, complexity, and availability of the underlying data. Apparel Group reviews and approves this plan at the end of Week 2, and the build proceeds against it.

The AWS Landing Zone (multi-account structure, identity federation, networking, and the security baseline) is owned and delivered by the AWS ProServe team. It is a dependency for the workstreams below, not part of Northbay's scope.

### Workstream 1: Data Foundation

The lakehouse platform that the use cases run on, built once and shared by all workstreams.

Activities

- Platform architecture baseline: account layout within the ProServe Landing Zone, storage and compute design, environment strategy.

- Lakehouse platform provisioning through infrastructure as code: S3 Tables with Apache Iceberg in a Bronze, Silver, and Gold medallion architecture, AWS Glue 5.0 Data Catalog, Lake Formation access control, Amazon MWAA orchestration, and CI/CD pipelines.

- Ingestion framework: reusable batch and CDC ingestion patterns for the in-scope sources.

- Source connectivity and ingestion to Bronze for the in-scope sources (Section 3.5), as access is granted.

- Silver layer conformance for the entities the use cases require (product, price, cost, sales, inventory, store).

- Gold layer datasets serving the Price Optimization, Inter-store Transfer, and Quick workstreams.

- Technical data quality checks at ingestion: completeness, record counts, and reconciliation against source.

- Observability: CloudWatch dashboards, alarms, and pipeline monitoring.

- Documentation, runbooks, and knowledge transfer.

Deliverables

- Deployed lakehouse platform: S3 Tables with Apache Iceberg (Bronze, Silver, Gold), Glue 5.0 Data Catalog, Lake Formation access control, MWAA orchestration, and CI/CD pipelines, all provisioned through infrastructure as code.

- Ingestion pipelines for the in-scope sources (Section 3.5), landing data into Bronze.

- Silver conformed entities (product, price, cost, sales, inventory, store) and Gold datasets serving the Price Optimization, Inter-store Transfer, and Quick workstreams.

- Ingestion-level data quality checks: completeness, record counts, and reconciliation against source.

- Observability dashboards and alarms for pipeline monitoring.

- Platform documentation, runbooks, and knowledge transfer to the Apparel Group technical team.

Assumptions

- The AWS Landing Zone is delivered by the AWS ProServe team and is available by the end of Week 2. Where it is available later, the platform build re-plans within the remaining weeks.

- AWS account access and IAM administration are granted in Week 1 per Section 6.1.

- Network connectivity decisions (VPN or Direct Connect) and firewall approvals for privately connected sources are made by Week 2, with any circuit procurement being Apparel Group's responsibility.

- Source-system access follows the extraction assumptions of the Price Optimization and Inter-store Transfer workstreams (Sections 3.2 and 3.3). For the remaining in-scope sources (Epsilon and MoEngage), the same conditions apply: extraction through a documented vendor API or file feed, without custom development, with credentials and schema documentation provided within 3 business days of kickoff, and with any vendor-mandated paid services being Apparel Group's responsibility.

Out of Scope

- The AWS Landing Zone (owned and delivered by AWS ProServe).

- Data governance frameworks, lineage tracking, data stewardship workflows, and master data management.

- Data quality remediation or cleansing inside upstream source systems.

- Onboarding of source systems beyond those listed in Section 3.5.

- Migration or decommissioning of existing data warehouse platforms.

### Workstream 2: Price Optimization

The initial build of the Price Optimization use case, covering Initial Pricing, Markup, and Markdown. The detailed scope and deliverables build on the SoW previously shared by Apparel Group and are finalized through the shared two-week discovery. What can be delivered within Phase 1 forms the Phase 1 scope; the remainder continues into Phase 2.

Activities

- Discovery (Weeks 1 to 2): source walkthroughs, data assessment, and use-case workshops with Apparel Group SMEs; definition of target state and definition of done; Phase 1 delivery plan for approval.

- Data extraction, profiling, and quality assessment (Weeks 3 to 5): land the pricing-relevant data into the lakehouse, profile history depth, grain, and completeness, and confirm what the data supports before model build.

- Use-case build (Weeks 5 to 10): data preparation and feature engineering, followed by the Initial Pricing, Markup, and Markdown capabilities defined in the approved delivery plan.

- Validation with Apparel Group business users (Weeks 11 to 12), then handover and knowledge transfer.

Assumptions

The scope, timeline, and effort for this workstream assume the following:

- Data from the in-scope sources can be extracted using each source's standard, supported, read-only extraction interfaces, without custom development: for Oracle RMS, JDBC access to the Data Access Schema views or an equivalent read replica; for Oracle XStore, DMS/CDC, a supported API, or a file extract; for Magento, a documented vendor API or file feed.

- Read credentials, access, and schema or data-dictionary documentation are provided within 3 business days of kickoff.

- The required history is available at the grain the use case needs: at minimum 24 months of sales, price, and markdown history at transaction grain.

- Source schemas are documented and stable. Reverse-engineering undocumented structures, or reconstructing history that is purged, overwritten, or retained only as current values, is not assumed.

- Extraction depends on no net-new licensing (for example, Oracle GoldenGate for DAS), vendor-mandated paid services, or new middleware. Any such procurement and its cost are Apparel Group's responsibility.

- In-scope data volumes fall within the range confirmed during discovery.

- Where these conditions hold, the Phase 1 build proceeds as scoped. Where any does not hold, whether identified during discovery or later in the build, the use case is re-baselined at that point to what the data supports within Phase 1, and the additional effort is carried into Phase 2 or addressed through a change request.

Out of Scope

- The complete Pricing Optimization Engine beyond the scope finalized and approved at the end of discovery (continued in Phase 2).

- Price execution or write-back into source systems.

- Data quality remediation or history reconstruction in upstream systems.

- Custom connector development for sources that do not meet the extraction assumptions above.

### Workstream 3: Inter-store Transfer

The initial build of the Inter-store Transfer use case, identifying stock that can be moved between stores to match supply to demand. The detailed scope and deliverables build on the SoW previously shared by Apparel Group and are finalized through the same shared two-week discovery, with the same approval at the end of Week 2. What can be delivered within Phase 1 forms the Phase 1 scope; the remainder continues into Phase 2.

Activities

- Discovery (Weeks 1 to 2): source walkthroughs, data assessment, and use-case workshops with Apparel Group SMEs; definition of target state and definition of done; Phase 1 delivery plan for approval.

- Data extraction, profiling, and quality assessment (Weeks 3 to 5): land the inventory, sales, and store data into the lakehouse, profile history depth, grain, and completeness, and confirm what the data supports before model build.

- Use-case build (Weeks 5 to 10): data preparation and feature engineering, followed by the transfer-recommendation capability defined in the approved delivery plan.

- Validation with Apparel Group business users (Weeks 11 to 12), then handover and knowledge transfer.

Assumptions

The scope, timeline, and effort for this workstream assume the following:

- Data from the in-scope sources can be extracted using each source's standard, supported, read-only extraction interfaces, without custom development: for Oracle RMS, JDBC access to the Data Access Schema views or an equivalent read replica; for Oracle SIM and XStore, DMS/CDC, a supported API, or a file extract.

- Read credentials, access, and schema or data-dictionary documentation are provided within 3 business days of kickoff.

- The required history is available at the grain the use case needs: at minimum 12 months of inventory position and movement history.

- Source schemas are documented and stable. Reverse-engineering undocumented structures, or reconstructing history that is purged, overwritten, or retained only as current values, is not assumed.

- Extraction depends on no net-new licensing, vendor-mandated paid services, or new middleware. Any such procurement and its cost are Apparel Group's responsibility.

- In-scope data volumes fall within the range confirmed during discovery.

- Where these conditions hold, the Phase 1 build proceeds as scoped. Where any does not hold, whether identified during discovery or later in the build, the use case is re-baselined at that point to what the data supports within Phase 1, and the additional effort is carried into Phase 2 or addressed through a change request.

Out of Scope

- The complete Inter-store Transfer capability beyond the scope finalized and approved at the end of discovery (continued in Phase 2).

- Execution of transfers in source systems (transfer orders, WMS or store operations integration).

- Data quality remediation or history reconstruction in upstream systems.

- Custom connector development for sources that do not meet the extraction assumptions above.

### Workstream 4: Amazon Quick (Retail IQ)

Amazon Quick ("Retail IQ") made available to business users for natural-language querying of operational and commercial data.

Activities

- Access to Amazon Quick from within the existing SIMS platform through an embedded link.

- Integration with the Microsoft 365 suite (Outlook, Teams, SharePoint and OneDrive) for workplace context.

- Connection to up to six data sources that are available within the Apparel Group AWS environment, confirmed by Apparel Group within the first two weeks. Priority is given to sources already resident in or accessible from AWS; sources landed in the lakehouse during Phase 1 qualify as they become available.

- Use-case workshops with business users to define the query patterns the connected data supports.

- Natural-language query across the connected data, with answers grounded in that data and source attribution, delivered for a single brand to prove the model end to end.

- Validation with business users, then handover.

Assumptions

- Apparel Group confirms the six data sources by the end of Week 2, and each confirmed source is resident in or accessible from the Apparel Group AWS environment at the time of connection, or becomes available through the Phase 1 lakehouse build. Where a confirmed source is not available when its connection is scheduled, the workstream re-plans within the remaining weeks and any work that no longer fits moves to Phase 2.

- Where a production database is required as a data source before it has been onboarded to the lakehouse, access is read-only and treated as an interim measure. A performance baseline is established before any queries run, query patterns are reviewed and approved to ensure no impact to business operations, and the connection is retired once the source is onboarded to the lakehouse. The team does not execute ad hoc or unvalidated queries against production systems.

- The SIMS platform team is available for the navigation integration in Weeks 3 to 5.

- Microsoft 365 tenant admin access for the productivity suite connectors is provided by Week 3.

Out of Scope

- The complete Amazon Quick implementation described in Section 7.2, including role-based access control across brands and countries, forecasting and predictive capabilities, root-cause analysis, coverage beyond a single brand, and personas beyond those agreed at kickoff.

- More than six data sources; additional sources constitute scope expansion.

- White-labeling of the Amazon Quick UI, which is not supported by the product; integration is via embedded link from SIMS.

- End-user BI dashboard development.

### Data Sources

The following sources are in scope for the Phase 1 use cases. The specific tables, fields, and history required from each are confirmed during discovery.

| # | Source | Domain |
| --- | --- | --- |
| 1 | Oracle Retail (RMS) | Merchandising, cost, item and location hierarchy |
| 2 | Oracle SIM | Store inventory positions |
| 3 | Oracle XStore | In-store sales transactions |
| 4 | Epsilon | Loyalty and customer master |
| 5 | MoEngage | Campaign and engagement data |
| 6 | Magento | E-commerce orders, customers, products |
| 7 | Vemco Footfall | Store footfall counts (optional) |
| 8 | Irisys Footfall | Store footfall counts (optional) |

## Project Schedule

Phase 1 runs over 12 weeks. It opens with the shared two-week discovery for Price Optimization and Inter-store Transfer, and the Phase 1 delivery plan is approved at the end of Week 2. The execution sequence within each retail workstream is deliberate: data is extracted, profiled, and quality-assessed in Weeks 3 to 5, before and alongside the early build, so that the use-case build proceeds on data whose depth, grain, and gaps are known. The Data Foundation platform build runs in Weeks 3 to 6 and delivers the ingestion framework that lands that data.

Milestones and dependencies

| Milestone | Owner | Due |
| --- | --- | --- |
| M1: AWS account and environment access granted | Apparel Group | Week 1 |
| M2: Source-system access, credentials, and schema documentation provided | Apparel Group | Within 3 business days of kickoff |
| M3: AWS Landing Zone available | AWS ProServe | End of Week 2 |
| M4: Phase 1 delivery plan approved (target state, definition of done, achievable scope) | Apparel Group | End of Week 2 |
| M5: Six Amazon Quick data sources confirmed | Apparel Group | End of Week 2 |
| M6: Microsoft 365 tenant admin access provided | Apparel Group | Week 3 |
| M7: Validation sign-off | Apparel Group | Week 12 |

12-week schedule by workstream

| Workstream / Activity | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Kickoff and mobilization | ● |  |  |  |  |  |  |  |  |  |  |  |
| Workstream 1: Data Foundation |  |  |  |  |  |  |  |  |  |  |  |  |
| Platform architecture baseline | ● | ● |  |  |  |  |  |  |  |  |  |  |
| Lakehouse platform build |  |  | ● | ● | ● | ● |  |  |  |  |  |  |
| Ingestion, Silver and Gold datasets for use cases |  |  |  | ● | ● | ● | ● | ● | ● | ● |  |  |
| Documentation and handover |  |  |  |  |  |  |  |  |  |  | ● | ● |
| Workstream 2: Price Optimization |  |  |  |  |  |  |  |  |  |  |  |  |
| Shared discovery | ● | ● |  |  |  |  |  |  |  |  |  |  |
| Delivery plan approved (M4) |  | ● |  |  |  |  |  |  |  |  |  |  |
| Data extraction, profiling and quality assessment |  |  | ● | ● | ● |  |  |  |  |  |  |  |
| Use-case build |  |  |  |  | ● | ● | ● | ● | ● | ● |  |  |
| Validation and handover |  |  |  |  |  |  |  |  |  |  | ● | ● |
| Workstream 3: Inter-store Transfer |  |  |  |  |  |  |  |  |  |  |  |  |
| Shared discovery | ● | ● |  |  |  |  |  |  |  |  |  |  |
| Delivery plan approved (M4) |  | ● |  |  |  |  |  |  |  |  |  |  |
| Data extraction, profiling and quality assessment |  |  | ● | ● | ● |  |  |  |  |  |  |  |
| Use-case build |  |  |  |  | ● | ● | ● | ● | ● | ● |  |  |
| Validation and handover |  |  |  |  |  |  |  |  |  |  | ● | ● |
| Workstream 4: Amazon Quick (Retail IQ) |  |  |  |  |  |  |  |  |  |  |  |  |
| Six data sources confirmed (M5) | ● | ● |  |  |  |  |  |  |  |  |  |  |
| SIMS embed and M365 integration |  |  | ● | ● | ● |  |  |  |  |  |  |  |
| Data source connectivity |  |  |  | ● | ● | ● | ● |  |  |  |  |  |
| Natural-language query, single brand |  |  |  |  |  | ● | ● | ● | ● |  |  |  |
| Validation and handover |  |  |  |  |  |  |  |  | ● | ● | ● | ● |

● active work in that week

Key dates

- End of Week 2: shared discovery complete; Phase 1 delivery plan approved by Apparel Group (M4). AWS Landing Zone available from ProServe (M3). Amazon Quick data sources confirmed (M5).

- Weeks 3 to 5: data extraction, profiling, and quality assessment for both retail use cases.

- Weeks 3 to 6: lakehouse platform build (a single shared platform serving all workstreams).

- Week 5: use-case build ramps on profiled, quality-assessed data.

- Weeks 11 to 12: validation and handover, close of Phase 1 (M7).

## Phase 1 Investment and Team

### Headline

| Item | Value |
| --- | --- |
| Phase 1 Total (AWS Funded), covering the Data Foundation, Price Optimization, Inter-store Transfer, and Amazon Quick workstreams |  |
| Duration | 12 weeks |
| Effective Team Size | ~8.5 FTE blended |

### Team Composition

| Role | Daily Rate (USD) | Allocation | Effort (Days) | Cost (USD) |
| --- | --- | --- | --- | --- |
| Datalake Lead (Tech Lead), Onsite | 900 | 100% | 19 |  |
| Datalake Lead (Tech Lead), Remote | 600 | 100% | 38 |  |
| AWS Data Lake Engineer (Senior) × 2 | 300 | 100% | 120 |  |
| Platform / DevOps Engineer (Senior) | 300 | 50% | 30 |  |
| ML Engineer (Retail Analytics) × 2 | 300 | 100% | 120 |  |
| GenAI Engineer | 300 | 100% | 60 |  |
| QA / Data Quality Engineer | 300 | 50% | 30 |  |
| Data Engineer | 300 | 100% | 60 |  |
| Project Manager | 300 | 50% | 30 |  |
| Total |  |  | ~507 |  |

### Notes on Pricing

- All figures are in USD, exclusive of applicable taxes.

- Phase 1 is fixed price for the scope defined in Section 3 and is fully funded by AWS.

- Work beyond the Phase 1 scope, or work continuing after the 12 weeks, is delivered by Northbay in Phase 2 and funded by Apparel Group on a time-and-material basis.

- The rates in Section 5.2 apply to Phase 1 only. Phase 2 rates are agreed separately as part of the Phase 2 engagement.

### Payment

Billing for Phase 1 follows the AWS ProServe billing mechanism.

## Client Responsibilities, Dependencies and Schedule Protection

Phase 1 is fixed in both duration and funding. Twelve weeks and the AWS-funded envelope do not extend, so the schedule depends on both sides meeting their commitments on time. This section sets out what Northbay needs from Apparel Group, the assumptions the plan rests on, and how the two teams handle it when something moves.

### Apparel Group Responsibilities

| # | Item | Required By |
| --- | --- | --- |
| 1 | AWS account access, IAM admin, and billing visibility | Week 1 |
| 2 | Project sponsor (single decision-maker) and weekly steering availability | Week 1 |
| 3 | Named technical owner for each in-scope source system (Section 3.5), with authority to grant access | Week 1 |
| 4 | Read credentials, connection details, and schema or data-dictionary documentation for all in-scope sources | Within 3 business days of kickoff |
| 5 | Business SMEs for the Price Optimization and Inter-store Transfer discovery workshops, available as needed until the delivery plan is approved | Weeks 1 to 2 |
| 6 | Confirmation of the six Amazon Quick data sources | End of Week 2 |
| 7 | Approval of the Phase 1 delivery plan for Price Optimization and Inter-store Transfer | End of Week 2 |
| 8 | Network connectivity decisions (VPN or Direct Connect) and firewall approvals for sources requiring private connectivity | Week 2 |
| 9 | SIMS platform team availability for the Amazon Quick navigation integration | Weeks 3 to 5 |
| 10 | Microsoft 365 tenant admin access for the productivity suite connectors | Week 3 |
| 11 | Validation participants and sign-off authority with 5 business day turnaround on reviews | Weeks 11 to 12, and throughout as needed |

### Assumptions

The Phase 1 plan rests on the following. The per-workstream assumptions in Section 3 apply in full and are part of this list.

- Access, credentials, and documentation are provided within the timelines in Section 6.1. Delays consume the fixed 12-week window; they do not extend it.

- The AWS Landing Zone is owned and delivered by the AWS ProServe team and is available by the end of Week 2. Where it is available later, the dependent workstreams re-plan within the remaining weeks.

- The in-scope sources are confirmed at kickoff and remain stable through Phase 1. Source substitution, schema changes, or system migrations during the engagement are handled as change requests.

- Apparel Group personnel respond to blocking decisions, access issues, and clarifications within 2 business days.

- Compliance, legal, or InfoSec reviews initiated by Apparel Group complete within 10 business days of submission.

- No restrictions are placed on Northbay's use of AWS-native services and standard AWS Lakehouse patterns unless agreed at kickoff.

- AWS account ownership and billing remain with Apparel Group, and AWS infrastructure run-cost is billed directly by AWS to Apparel Group.

- Third-party system owners and vendors cooperate with reasonable integration requests. Vendor-mandated paid services to enable access are Apparel Group's responsibility.

- Defects originating in upstream source data quality, rather than in Northbay-built pipelines, are tracked separately and do not block validation sign-off.

- The team composition and rates in Section 5.2 hold for the duration of Phase 1.

### How Delays and Changes Are Handled

The governing principle is simple: Phase 1 delivers whatever the fixed 12-week, AWS-funded envelope allows. Where a dependency arrives late, an assumption does not hold, or scope grows, the affected work is not lost; it moves into Phase 2, where it is delivered on a time-and-material basis.

| Situation | How It Is Handled |
| --- | --- |
| Access, credentials, or documentation arrive later than the Section 6.1 timelines | Northbay flags the delay in the weekly steering call and the shared RAID log. The affected workstream is re-planned within the remaining weeks. Work that no longer fits in Phase 1 as a result moves to Phase 2. |
| A workstream data-extraction assumption (Sections 3.2 and 3.3) does not hold for a source, whether identified during discovery or later in the build | The affected use case is re-baselined at that point to what the data supports within Phase 1. The remaining depth is delivered in Phase 2. |
| The AWS ProServe Landing Zone is available later than the end of Week 2 | The dependent workstreams re-plan within the remaining weeks; work that no longer fits moves to Phase 2. |
| Scope additions requested during Phase 1 | Documented as a change request, and delivered in Phase 2 unless both parties agree it displaces existing Phase 1 scope. |
| Source substitution after kickoff | Documented as a change request with assessed effort. The substituted work is scheduled into Phase 2 where it does not fit the remaining Phase 1 window. |
| SME or sign-off availability gaps beyond Section 6.1 commitments | Flagged in steering. Where the gap stalls a workstream for more than 5 cumulative business days, the affected deliverables are re-scoped to Phase 2. |
| Force majeure | Schedule paused for the duration; the parties agree a restart plan. |

No change proceeds without written agreement from both parties, and nothing is silently dropped: everything either lands in Phase 1 or is explicitly carried into Phase 2.

### Communication and Escalation

- Weekly steering call with the Apparel Group sponsor covering status, risks, blockers, and decisions needed.

- Shared RAID log maintained by Northbay and visible to Apparel Group throughout. All access requests, schema requests, and dependency commitments are tracked there with dates.

- Any blocker open more than 3 business days escalates to steering; more than 5 business days, to the executive sponsors on both sides.

## Phase 2 Roadmap

Phase 2 is a direct continuation of Phase 1, funded by Apparel Group on a time-and-material basis. It takes the Phase 1 use cases to the complete scope defined in the SoWs shared by Apparel Group and extends the platform across the wider Apparel Group landscape. Phase 2 includes, but is not limited to, the following.

### Retail Use Cases at Complete Scope

- Pricing Optimization Engine: , covering Initial Pricing, Markup, and Markdown to the complete scope defined in the SoW shared by Apparel Group, continuing from the Phase 1 build.

- Inter-Store Transfer: to its complete scope, continuing from the Phase 1 build.

- Initial Allocation.

- Assortment Planning and MFP.

### Amazon Quick Implementation

The complete Amazon Quick implementation, delivering the solution defined in the SimsGPT and RetailIQ SoWs, used as the baseline for scope, features, and functionality, rebranded under the SIMS ecosystem and hosted within a unified SIMS platform. The platform enables real-time business insights and decision-making, including role-based access control, through integration with enterprise data sources and the Lakehouse architecture, supporting both conversational AI and proactive intelligence across operational, commercial, and strategic use cases. It integrates with Microsoft Teams, Outlook, ShareDrive, and other enterprise tools so that insights, collaboration, and actions happen within existing workflows. The objective is a centralized AI-powered platform for business intelligence, decision support, productivity, and enterprise knowledge management within a single integrated ecosystem.

### Enterprise-Wide Data Lake

- Onboarding of the remaining source landscape across retail, e-commerce, loyalty, marketing, supply chain, finance, and HR systems.

- Expansion of the Silver and Gold layers to support the complete use-case catalogue.

- Data quality, governance, lineage tracking, and master data management matured across the estate.

- Self-service analytics for brand and business teams on governed datasets.

The detailed scope, sequencing, and effort for Phase 2 are agreed between Apparel Group and Northbay as Phase 1 progresses, informed by the discovery outcomes and the operational experience of the Phase 1 build.

## Out of Scope (Phase 1)

Per-workstream exclusions are listed with each workstream in Section 3. In addition, the following are out of scope for Phase 1 across the program and are addressed in Phase 2 or through separate engagements:

- The AWS Landing Zone, which is owned and delivered by the AWS ProServe team.

- Initial Allocation, Assortment Planning and MFP.

- Data governance frameworks, lineage tracking, and master data management across the estate.

- Data quality remediation, cleansing, or reconstruction of history in upstream source systems.

- Migration or decommissioning of existing data warehouse platforms.

- Production support and 24x7 operations, which can be covered under a separate managed services engagement if required.

- Mobile or web application development consuming the data lake.

## Next Steps

- Proposal review and sign-off by the Apparel Group sponsor.

- Kickoff workshop to confirm source-system owners, grant access, and mobilize the four workstreams.

- Shared discovery begins for Price Optimization and Inter-store Transfer, coordinated with the AWS ProServe Landing Zone delivery.

- Project mobilization within 2 weeks of sign-off.